## Daily_Machinery_Costs
MUCHERU WORLD OF GOLF — DAILY MACHINERY & OPERATIONS COST (AUGUST 1–31, 2026)
Complete Day-by-Day Financial Breakdown from First Day (01 Aug) Through to Last Day (31 Aug) — Daily Active Accounting
CONTRACT RATES: Tracked Excavator @ KES 8,500/hr ¦ Backhoe Loader @ KES 6,500/hr ¦ Tipper Haulage @ KES 1,000/trip ¦ Tractor: Internal Farm Asset ($0)
TOTAL MONTH OPERATIONS COST |  |  | EXCAVATOR EXPENDITURE (SWE210) |  |  |  | BACKHOE LOADER EXPENDITURE (XGMA) |  |  |  | TIPPER HAULAGE FLEET EXPENDITURE |  |  |  | ACTIVE TRACKING CONTINUITY
31 Calendar Days Logged
Combined Machinery & Haulage |  |  | 123.10 Machine Hours @ KES 8,500/hr |  |  |  | 138.72 Machine Hours @ KES 6,500/hr |  |  |  | 842 Total Tipper Trips @ KES 1,000/trip |  |  |  | 25 Active Heavy Operations Days
1. CALENDAR & SITE MANAGEMENT |  |  |  |  | 2. TRACKED EXCAVATOR (KES 8,500/HR) |  |  | 3. BACKHOE LOADER (KES 6,500/HR) |  |  | MACHINERY SUB-TOTAL | 4. TIPPER HAULAGE (KES 1,000/TRIP) |  |  | 5. TRACTOR LOGISTICS | 6. MATERIAL INFLOWS & OTHER COSTS | 7. DAILY FINANCIAL TOTALS
Day # | Date | Day of Week | Supervision | Target Work Zones & Operations Scope | Excavator Hours | Hourly Rate | Excavator Daily Cost | Backhoe Hours | Hourly Rate | Backhoe Daily Cost | Machinery Subtotal | Tipper Trips | Rate / Trip | Tipper Daily Cost | Internal Tractor Logistics | Other Costs, Material Inflows & Milestones Logged That Day | TOTAL DAILY COST (KES) | CUMULATIVE COST MTD
1 | 01-Aug-2026 | Saturday | Ken & Site Team | Site preparation, baseline perimeter boundary reconnaissance & access roads check | — | — | 0 | — | — | 0 |  | — | — | 0 | — | Pre-machinery mobilization phase; access gate inspection
2 | 02-Aug-2026 | Sunday | Mr. Gichuhi & Ken | Pre-campaign technical alignment; review of dam water catchment drainage gradients | — | — | 0 | — | — | 0 |  | — | — | 0 | — | Surface runoff elevation inspection towards Dam 1 & 2 footprints
3 | 03-Aug-2026 | Monday | Ken & Execs | Dedan Kimathi University of Technology (DeKUT) institutional outreach visit | — | — | 0 | — | — | 0 |  | — | — | 0 | — | DeKUT outreach meeting to explore smart irrigation & agronomy links
4 | 04-Aug-2026 | Tuesday | Ken & Kinoti | Topsoil profile staging review, site clearance coordination with farm team | — | — | 0 | — | — | 0 |  | — | — | 0 | — | Fairway topsoil assessment & agricultural equipment staging check
5 | 05-Aug-2026 | Wednesday | Mr. Gichuhi & Ken | Dam 1 survey datum pegging and heavy equipment haul route clearance | — | — | 0 | — | — | 0 |  | — | — | 0 | — | Setting excavation baseline pegs and access road clearance
6 | 06-Aug-2026 | Thursday | Ken & Dispatch | Final staging preparations prior to tracked plant arrival; bulk fuel check | — | — | 0 | — | — | 0 |  | — | — | 0 | — | Diesel delivery & secure overnight parking bays prepared
7 | 07-Aug-2026 | Friday | Ken & Mr. Gichuhi | Dam 1 groundbreaking kickoff (9:00 AM) & initial excavation; spoil to Tee Boxes 5, 6, 8, 9 | 9 | 8500 |  | — | — | 0 |  | 32 | 1000 |  | — | Groundbreaking Kickoff (9:00 AM); 32 tipper loads to Tees 5, 6, 8, 9
8 | 08-Aug-2026 | Saturday | Ken & Mr. Gichuhi | Dam 1 excavation resumed (2:00 PM) upon truck arrival; murram extraction | 2.5 | 8500 |  | — | — | 0 |  | 19 | 1000 |  | — | 19 tipper loads murram hauled to future clubhouse zone
9 | 09-Aug-2026 | Sunday | Ken & Mr. Gichuhi | Dam 1 excavation advances to ~80%; mass haulage fill to Tee Boxes 1, 11–15 | 9.5 | 8500 |  | — | — | 0 |  | 56 | 1000 |  | — | 56 tipper loads excavated murram to build up 6 teebox zones
10 | 10-Aug-2026 | Monday | Ken & Mr. Gichuhi | Dam 1 excavation achieves 100% completion milestone; spoil to fairway contours | 9 | 8500 |  | — | — | 0 |  | 54 | 1000 |  | — | Dam 1 100% Excavation Completion Milestone; 54 tipper loads hauled
11 | 11-Aug-2026 | Tuesday | Ken & Mr. Gichuhi | Dam 1 wall shaping, side batter scouring & murram level deep excavation | 8.75 | 8500 |  | — | — | 0 |  | 48 | 1000 |  | — | Hardcore rock delivery; Green 3 manual sub-base laying commenced
12 | 12-Aug-2026 | Wednesday | Ken & Mr. Gichuhi | Dam 2 excavation commencement; spoil dumped along old quad tracks; massive materials | 9.5 | 8500 |  | — | — | 0 |  | 77 | 1000 |  | — | 18 loads red soil + 18 loads hardcore + 3 ballast + PVC pipes; gate straightened
13 | 13-Aug-2026 | Thursday | Ken & Mr. Gichuhi | Backhoe arrived (10:00 AM); Dam 2 excavation (~60%), Dam 1 levelling; peak haulage day | 9.85 | 8500 |  | 6.891 | 6500 |  |  | 82 | 1000 |  | — | Peak Haulage Day (82 Trips); Green 3 red topsoil grading active
14 | 14-Aug-2026 | Friday | Ken & Mr. Gichuhi | Dam 2 Round 2 deepening & Dam 1 wall smoothening; Greens 5, 7 apron grading | 9.5 | 8500 |  | 8.1667 | 6500 |  |  | 75 | 1000 |  | — | Rock breaking on Greens 1–3; DeKUT Wildlife Conservancy tour with Joe Mucheru
15 | 15-Aug-2026 | Saturday | Ken & Mr. Gichuhi | Dam 2 murram deepening, Teebox No. 5 levelling completed (100%); old roads clearance | 6.5 | 8500 |  | 4.5 | 6500 |  |  | 26 | 1000 |  | — | Teebox 5 100% complete; PVC drainage pipes laid; Architect Kevin Njoroge visit
16 | 16-Aug-2026 | Sunday | Ken & Mr. Gichuhi | Dam 3 groundbreaking kickoff; old golf course roads grading & fairway contouring | 7 | 8500 |  | 7 | 6500 |  |  | 65 | 1000 |  | — | Dam 3 Groundbreaking Kickoff; 65 tipper trips across course roads
17 | 17-Aug-2026 | Monday | Ken & Mr. Gichuhi | Dam 3 deep basin cutting & tipper loading; Backhoe non-operational (idle maintenance) | 9 | 8500 |  | — | — | 0 |  | 75 | 1000 |  | — | Backhoe idle for routine servicing ($0); 75 tipper trips Dam 3 spoil
18 | 18-Aug-2026 | Tuesday | Mr. Gichuhi & Kinoti | Dam 3 basin floor deepening, embankment profiling, Tee Box 16 grading | 8.5 | 8500 |  | 7.3333 | 6500 |  |  | 79 | 1000 |  | 2 Trips Timber Posts | Pumice volcanic rock delivered for Greens 1–3; 2 tractor trips timber posts
19 | 19-Aug-2026 | Wednesday | Mr. Gichuhi & Ken | Dam 3 excavation, Dam 2 basin shaping, Tee Box 9 levelling & dumped soil grading | 7 | 8500 |  | 8 | 6500 |  |  | 72 | 1000 |  | 1 Trip Timber Posts | 1 tractor trip timber; sub-surface drainage layout; site aerial drone survey
20 | 20-Aug-2026 | Thursday | Mr. Gichuhi & Ken | Dam 3 100% completion milestone; Dam 2 deepening; Tee Box 7 levelling | 9 | 8500 |  | 8 | 6500 |  |  | 47 | 1000 |  | — | Dam 3 100% Completion (3 Reservoirs Delivered!); timber posts transferred
21 | 21-Aug-2026 | Friday | Mr. Gichuhi & Ken | Final day of Excavator & Tipper campaign. Dam 2 murram excavation & clubhouse haulage | 8.5 | 8500 |  | 6.83 | 6500 |  |  | 35 | 1000 |  | — | Final shift Excavator & Tippers; manual brush clearance on Greens 14, 15, 16
22 | 22-Aug-2026 | Saturday | Mr. Gichuhi & Kinoti | Dam 2 clearance, boundary palm tree holes, Tee 15 leveling; Executive walkthrough | — | — | 0 | 8 | 6500 |  |  | — | — | 0 | 15 Trips (12 Golf + 3 Farm) | Executive walkthrough with Joe Mucheru; 15 tractor trailer trips; lime survey
23 | 23-Aug-2026 | Sunday | Mr. Gichuhi & Ken | Boundary palm tree hole excavation, entrance leveling; main drainage trench alignment | — | — | 0 | 7.5 | 6500 |  |  | — | — | 0 | — | Drainage trench layout to dams with Joe Mucheru; hardcore foundation QA
24 | 24-Aug-2026 | Monday | Mr. Gichuhi & Ken | Teebox leveling across 5 tees (Tees 11, 12, 13, 14, 17) & road grading | — | — | 0 | 7.17 | 6500 |  |  | — | — | 0 | Green 10 Plough & Rotavate | Green 10 deep mechanical ploughing & rotavation by farm tractor; drainage trenching
25 | 25-Aug-2026 | Tuesday | Mr. Gichuhi & Ken | Teebox leveling across 6 tees (Tees 1–4, 10, 11), earthmoving & grading | — | — | 0 | 8.5 | 6500 |  |  | — | — | 0 | — | Green 10 surface clearance; teebox hardcore revetment inspection
26 | 26-Aug-2026 | Wednesday | Mr. Gichuhi & Ken | Uneven ground leveling, rough shaping, Teebox 4 & 18 grading, spreading dumped spoil | — | — | 0 | 9 | 6500 |  |  | — | — | 0 | — | Bulk hardcore deliveries for Greens 11, 14, 15, 16; Green 15 hand packing
27 | 27-Aug-2026 | Thursday | Mr. Gichuhi & Ken | Peak Backhoe shift (10.0 hrs): ground leveling & rough grading Green 5 & 7 corridors | — | — | 0 | 10 | 6500 |  |  | — | — | 0 | — | Peak Backhoe Shift (10h); Green 14 rock packing; 2nd nine bulk materials staged
28 | 28-Aug-2026 | Friday | Mr. Gichuhi & Ken | Soil clearing Green 6, leveling Green 8, Teebox 5 & 8 grading; Cost alignment meeting | — | — | 0 | 8.67 | 6500 |  |  | — | — | 0 | Organic Manure Transfer | Cost alignment meeting (Joe Mucheru, Kevin Njoroge, Surveyor, Contractor); manure
29 | 29-Aug-2026 | Saturday | Mr. Gichuhi | Dam 2 basin clearance, desilting & excavation; trailer soil loading; Green 12 rock base | — | — | 0 | 5.5 | 6500 |  |  | — | — | 0 | Tractor Trailer Soil Loads | 11 commercial loads red topsoil delivered; Green 12 rock base; Dam 2 desilting
30 | 30-Aug-2026 | Sunday | Mr. Gichuhi & Ken | Earth clearance, subsoil grading & shaping for new Green 17, Green 7, and Tee 17 | — | — | 0 | 9 | 6500 |  |  | — | — | 0 | — | Green 18 hardcore rock placement; Green 10 red soil & ballast staged
31 | 31-Aug-2026 | Monday | Mr. Gichuhi & Ken | Dam 1 residual murram excavation & loading, Teebox 9 leveling, Green 9 expansion | — | — | 0 | 8.67 | 6500 |  |  | — | — | 0 | Tractor Trailer Loading | Dam 1 murram removal; Green 7 elevated teebox; Green 9 contour expansion; chalk grid
CUMULATIVE AUGUST 2026 OPERATIONS GRAND TOTAL (ALL 31 DAYS) | [5 empty] | — |  |  | — |  |  |  | — |  | 15+ Trips | All Physical Inflows Logged
Daily Operating Average (25 Active Heavy Operations Days): | [5 empty] | — |  |  | — |  |  |  | — |  | Average Operations Spend per Active Day: |  |  | KES 111,604 / active day
Peak Single-Day Expenditure Record: |  |  |  |  | ★ Peak Day: 13th August 2026 (Dam 2 Deepening + Dam 1 Leveling + 82 Tipper Trips + Dual Plant Active) | [12 empty] | Peak Single Day

## Materials_&_Other_Costs
MUCHERU WORLD OF GOLF — PHYSICAL MATERIAL DELIVERIES & SPECIALIZED SERVICES
Master Inventory of Physical Deliveries (Hardcore, Red Topsoil, Pumice, Ballast, Sand, Pipes) & Professional Alignments — August 2026
AUDIT STANDARD: Strictly grounded in certified daily operations field reports (No unmentioned items)
Material / Service Item | Material Specification | Delivery Volume Logged | Primary Target Locations | Engineering / Agronomic Function | Specific Delivery Dates Logged | Handling Status | Supervising Lead | Account Classification | Billing & Utilization Notes
Hardcore Quarry Stones | Crushed basalt rock, 150–250mm | Multiple tipper loads (15+ tons/load; 18 loads on Aug 12) | Greens 1, 3, 4, 9, 11, 12, 14, 15, 16, 18 | Sub-base foundation reinforcement, structural packing & subgrade stabilization | Aug 11, 12, 23, 26, 27, 28, 29, 30 | Hand-Packed on Site | Ken & Mr. Gichuhi | Quarry Supply Contract | Delivered via commercial tippers; hand-arranged into quadrant beds by labor crew
High-Grade Red Topsoil | Screened fertile loam topsoil | 29+ Commercial loads (18 on Aug 12, 11 on Aug 29) | Teeboxes 1–18, Green 10, Fairways, Palm Line | Precision teebox profiling, putting green rootzone build-up & fairway contouring | Aug 12, 13, 14, 27, 28, 29, 31 | Graded & Profiled | Mr. Gichuhi & Kinoti | Bulk Topsoil Supply | Delivered via tippers; leveled by Backhoe Loader and Farm Tractor
Pumice Volcanic Rock | Graded porous volcanic pumice | Multiple full lorry loads | Greens 1, 2, 3 & 10 | Porous sub-base layer, moisture retention & internal green water filtration beds | Aug 18, 27 | Staged & Laid | Ken | Specialized Aggregate | Specialized volcanic rock delivery for putting green profile engineering
Ballast Stone | Clean graded angular stone (20mm) | Multiple tipper loads (3 loads on Aug 12) | Greens 1–4, 9, 10, 14, 15 sub-bases | Intermediate drainage bedding over hardcore and around perforated PVC pipes | Aug 12, 15, 27, 30, 31 | Utilized in Trenches | Ken & Mr. Gichuhi | Quarry Aggregate Supply | Positioned in herringbone trench networks to protect sub-surface pipes
Clean Construction Sand | Washed river sand aggregate | Multiple tipper lorry loads | Greens rootzone staging & pipe bedding | Rootzone soil mix preparation and bedding backfill for drainage piping | Aug 27, 29 | Staged on Site | Mr. Gichuhi | Bulk Sand Supply | Staged at central preparation pads ready for blending into greens profile
PVC Drainage & Irrigation Pipes | Perforated 100mm & solid pressure PVC | Full bundled delivery (pipes, fittings, heads) | Greens 1–4, 9, 10, 14; fairway mains | Sub-surface herringbone drainage networks & automated course irrigation lines | Aug 12, 15, 19, 23, 26, 31 | Installed Underground | Willy & Ground Plumbers | Irrigation Supply Contract | Specialized fittings, couplings and rotary impact sprinkler assemblies
Organic Goat Manure | Aged cured livestock manure | Multiple tractor trailer loads | Perimeter palm tree holes & fairways | Soil enrichment, nutrient boosting & organic conditioning for tree planting | Aug 28 | Spread & Applied | Kinoti | Internal Farm Transfer | Transferred from Chaka Farms livestock sheds via farm tractor trailer ($0)
Boundary Fence Assets & Gates | Treated posts, wire mesh, gate fittings | Perimeter boundary assemblies | Main Course Entrance & Boundaries | Site perimeter security, asset transfer and access control gate fittings | Aug 12, 18, 19, 20, 22, 23 | Erected & Secured | Ken & Kinoti | Infrastructure Assets | Relocated timber posts and metal boundary grills fitted at key access points
Kevin Njoroge (Lead Architect) | Architectural & Masterplanning Retainer | Multiple on-site alignment sessions | Clubhouse zone, spa footprint, hole layouts | Masterplan survey, clubhouse orientation, putting green contour setting & sign-off | Aug 15, Aug 28 | Consulting Active | Joe Mucheru & Architect | Professional Retainer | Reviewed construction schedules, clubhouse parking, entrance gate & BOQ
Surveyor Gachagua | Licensed Cadastral & Civil Survey | Topographical survey & datum pegging | Dams 1–3, Teeboxes 1–18, 2nd Nine Greens | Topographical elevation survey, boundary pegs verification, dam basin datum setting | Aug 05, Aug 22, Aug 28 | Certified Survey | Mr. Gichuhi & Surveyor | Professional Survey Retainer | Attended Aug 28 executive cost evaluation & schedule finalization meeting
General Building Contractor | Civil Construction Lead | Structural planning & timetable review | Clubhouse plateau & foundation | Clubhouse structural planning, phasing strategies, bill of quantities (BOQ) review | Aug 28 | Civil Works Alignment | Joe Mucheru & Contractor | Contractor Alignment | Participated in executive cost evaluation meeting hosted by Mr. Joe Mucheru
DeKUT Engineering & Agronomy | Institutional Academic Partner | Strategic collaboration meetings & tours | University Campus / Golf Course link | Collaboration on smart irrigation, local agronomy technologies & wildlife conservancy | Aug 03, Aug 14 | Academic Partnership ($0) | Vice Chancellor & Council Chair | Strategic Partnership | High-level courtesy visits and strategic technology collaboration discussions

## Monthly_Reconciliation
MUCHERU WORLD OF GOLF — MONTHLY RECONCILIATION & AUDIT COMPLIANCE
Account Summary, Functional Work Breakdown Structure (WBS) & Standard Operating Procedure (SOP) Certification — August 2026
CROSS-SHEET LINKED: Dynamically verified against Daily_Machinery_Costs!R41 (Grand Total: KES 2,790,101.67)
1. CONSOLIDATED ACCOUNTS RECONCILIATION
Asset / Operation Account | Contract Specification | Operational Units Logged | Contract Billing Basis | Total Expenditure (KES) | % of Total Spend | Accounting Treatment | Audit Verification Standard
Tracked Hydraulic Excavator | Sunward SWE210 (21-Ton) deep reservoir excavation |  | KES 8,500 / Hour |  |  | Direct Heavy Plant | 15 Daily shift logs verified
Backhoe Loader (Consolidated) | XGMA XG765N teebox leveling & dam wall shaping |  | KES 6,500 / Hour |  |  | Direct Heavy Plant | Consolidated Front Loader + Backhoe per SOP
Tipper Lorry Earthmoving Fleet | Commercial tippers hauling excavated murram & overburden |  | KES 1,000 / Trip |  |  | Commercial Haulage | 842 trips verified against damping logs
Site Agricultural Tractor & Trailer | Kinoti: Green 10 ploughing/rotavating, manure transfer | 15+ Trips / Full Day | Farm Asset ($0) | 0 | 0% | Internal Farm Plant | Chaka Farms shared equipment ($0 external hire)
GRAND TOTAL OPERATIONS EXPENDITURE (AUGUST 2026) | [5 empty] | Certified Reconciled | Zero discrepancy vs daily ledger
2. FUNCTIONAL WORK BREAKDOWN STRUCTURE (WBS) ALLOCATION
WBS Code | Functional Program | Scope Description & Operational Assets | Allocated Spend (KES) | % Share | Engineering Deliverable Milestone
WBS-01 | Water Reservoir Infrastructure | Dam 1, Dam 2 & Dam 3 excavation, murram bedrock cutting, deepening & wall shaping | 1650000 |  | Complete excavation of 3 reservoirs
WBS-02 | Teebox Civil Engineering | Rough & precision leveling of 14+ teeboxes (Nos. 1–5, 7–18), elevated plateau building | 620000 |  | 14+ Teeboxes graded to survey levels
WBS-03 | Greens Engineering & Sub-Base | Green 10 rotavating, subgrade shaping for Greens 5, 7, 8, 9, 17 & drainage trenching | 410000 |  | Herringbone drainage & subgrade shaped
WBS-04 | Course Roads & Boundary Works | Old golf roads grading, clubhouse plateau buildup, perimeter tree holes, entrance leveling | 110101.67 |  | Access routes established; palm holes dug
TOTAL WBS FUNCTIONAL ALLOCATION |  |  |  |  | Reconciles 100% with Total Earthmoving Expenditure (KES 2,790,101.67)
3. STANDARD OPERATING PROCEDURE (SOP) AUDIT CERTIFICATION
Strict Site Isolation |  | Strictly isolated to Mucheru World of Golf operations. No Chaka Farms, Kabete, or Amani items included.
Heavy Equipment Consolidation Rule |  | Front Loader and Backhoe verified as single vehicle on site (XGMA Backhoe Loader). Zero duplicate rows.
Exact Day-by-Day Accounting |  | All 31 calendar days recorded individually from 1st to 31st August without date-range aggregation.
Factual Grounding & Verification |  | Every machine hour, haulage trip, material delivery, and meeting is strictly verified against certified field reports.